## Progress Report
Progress Report Updated On : |  |  |  | 20/07/2026
Project : |  |  |  | Cooley Shanghai Meeting Room Retrofit
Cable installation
Item No. | Description | Demolition |  |  | Protection |  |  | Restoration |  |  | New Point Wiring |  |  | Testing |  |  | Labelling |  |  | System trial operation |  |  | Overall Percentage
| Floor | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date
L35
1 | Reception and large conference room | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-17 | 2026-07-17 | [15 empty] | 100%
2 | Central Park | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-19 | 2026-07-19 |  |  |  | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-20 | 2026-07-20 | 100%
3 | 103 | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-19 | 2026-07-19 |  |  |  | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-20 | 2026-07-20 | 100%
4 | Open office | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-20 | 2026-07-20 | 100%
Overall Percentage (%)
|  | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-17 | 2026-07-17 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-19 | 2026-07-19 | 100% | 2026-07-20 | 2026-07-20 | 100%
Coming Soon:- Targeted Progress on within this week
In Progress
Delay
Not Started
Completed

## Site Photo
Progress Report Updated On : |  |  | 20/07/2026
Project : |  |  | Cooley Shanghai Meeting Room Retrofit
Item No. | Date | Description | Photos
1 | 17/07/2026 | Reception Area - Before cable removal (前台区域工位布线拆除前)
2 | 17/07/2026 | Reception Area - Cable removal in progress (拆除过程中)
3 | 17/07/2026 | Reception Area - Cable labelled & coiled under floor (线缆整理标记盘放地板下)
4 | 19/07/2026 | Reception Area - Cable termination T568B (线缆端接)
5 | 19/07/2026 | Reception Area - Continuity test passed (通断测试通过)
6 | 19/07/2026 | Reception Area - Panel installed with labels (面板安装+标签)
7 | 19/07/2026 | New points for wiring(新增点位穿线)
8 | 19/07/2026 | Side Door - New card reader installed by security vendor (安防新增读卡器)
9 | 19/07/2026 | Side Door - Security cable relocation assisted (协助安防线缆移线)
10 | 20/07/2026 | System commissioning & test (系统试运行)
11 | 20/07/2026 | Completion documentation (竣工资料编制)

## Issue_RFA Log
ISSUE LOG
Project : |  | Cooley Shanghai Meeting Room Retrofit
Item No. | Date | Issue Description | Risk | Proposed solution | Action By | Completed Photos | Issue Open / Closed | Remarks
1 | 19/07/2026 | Security vendor installed new card reader at side door on Sunday. Assisted with security cable relocation (network cable left in place). Monday on-site commissioning support. (安防单位周日新增侧门读卡器，协助安防移线，周一试运行保障) | Low | Network cable retained at original position, security cable rerouted to new location. (网线留原处，安防线缆重新布放) | Cailleach |  | Closed | Completed with security vendor
2 | 20/07/2026 | Network switch port not activated at site. Coordinated with JACK. (现场网络交换机端口未开通，已和JACK沟通) | Medium | Coordinate with IT to activate switch port. (协调IT开通交换机端口) | Cailleach |  | Open | Pending JACK confirmation
3 | 20/07/2026 | Open area workstation - no network faceplate, only bare module. No compatible panel found at nearby hardware stores. Module left as-is to ensure next-day operation. (开放区域工位无网络面板，原为裸模块，附近五金店无适配面板，暂按原有方式放置) | Low | Source compatible faceplate and install during next site visit. (下次进场采购适配面板安装) | Cailleach |  | Open | Temporary - follow up required
4 | 20/07/2026 | Century Park MTR - network cable insufficient length. Module terminated under floor, jumper routed to cable tray under desk. (世纪公园会议室网络线缆长度不够，模块留在地板下，跳线至桌面下方理线槽) | Low | Acceptable via jumper. Update as-built. (跳线方案可接受，更新竣工图) | Cailleach |  | Open | As-built to be updated
RFI / RFA LOG
Project : |  | Cooley Shanghai Meeting Room Retrofit
Item No. | Issued Date | RFI / RFA | Description | Issued to | Respond by |  | Issue Open / Closed | Remarks
1