## Progress Report
Progress Report Updated On :
Project :
L35 Office Retrofit (35F),font.bold=True,font.size=14pt,font.name=Arial,font.color=FFFFFFFF,fill=FF0099FF,border.left=medium,border.right=medium,border.top=medium,border.bottom=medium,alignment.horizontal=center,alignment.vertical=center,alignment.wrapText=True,merge=C12:Q12
Item No. | Description | Cable Pulling,font.bold=True,font.size=10pt,font.name=Arial,font.color=FFFFFFFF,fill=FF0099FF,border.left=medium,border.top=medium,border.bottom=medium,alignment.horizontal=center,alignment.vertical=center,alignment.wrapText=True,merge=C13:E13 |  |  | Termination |  |  | Faceplate Installation |  |  | Testing |  |  | Labelling
| Floor | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date
35F
1 | Reception | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 0%
2 | Open Office | 100% | 20/07/2026 | 20/07/2026 | 100% | 20/07/2026 | 20/07/2026 | 100% | 20/07/2026 | 20/07/2026 | 100% | 20/07/2026 | 20/07/2026 | 100% | 20/07/2026 | 20/07/2026 | 0%
3 | Executive Office 1 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 0%
4 | Executive Office 2 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 0%
5 | Executive Office 3 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 0%
6 | Meeting Room | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 100% | 19/07/2026 | 19/07/2026 | 0%
Overall Percentage (%)
100%
Coming Soon:- Targeted Progress on within this week

## Site Photo
Progress Report Updated On : |  |  | 20/07/2026
Project : |  |  | L35 Office Retrofit
Item No. | Date | Description | Photos
1 | 19/07/2026 | Reception - Before cable pulling (穿线前)
2 | 19/07/2026 | Reception - Cable pulling completed (穿线完成)
3 | 19/07/2026 | Reception - Termination in progress (端接过程)
4 | 19/07/2026 | Reception - Termination completed (端接完成)
5 | 19/07/2026 | Reception - Faceplate installed (面板安装)
6 | 19/07/2026 | Reception - Test passed (测试通过)
7 | 19/07/2026 | Reception - Labels completed (标签完成)
8 | 20/07/2026 | Open Office - Before cable pulling (穿线前)
9 | 20/07/2026 | Open Office - Cable pulling completed (穿线完成)
10 | 20/07/2026 | Open Office - Termination in progress (端接过程)
11 | 20/07/2026 | Open Office - Termination completed (端接完成)
12 | 20/07/2026 | Open Office - Faceplate installed (面板安装)
13 | 20/07/2026 | Open Office - Test passed (测试通过)
14 | 20/07/2026 | Open Office - Labels completed (标签完成)
15 | 19/07/2026 | Executive Office 1 - Before cable pulling (穿线前)
16 | 19/07/2026 | Executive Office 1 - Cable pulling completed (穿线完成)
17 | 19/07/2026 | Executive Office 1 - Termination in progress (端接过程)
18 | 19/07/2026 | Executive Office 1 - Termination completed (端接完成)
19 | 19/07/2026 | Executive Office 1 - Faceplate installed (面板安装)
20 | 19/07/2026 | Executive Office 1 - Test passed (测试通过)
21 | 19/07/2026 | Executive Office 1 - Labels completed (标签完成)
22 | 19/07/2026 | Executive Office 2 - Before cable pulling (穿线前)
23 | 19/07/2026 | Executive Office 2 - Cable pulling completed (穿线完成)
24 | 19/07/2026 | Executive Office 2 - Termination in progress (端接过程)
25 | 19/07/2026 | Executive Office 2 - Termination completed (端接完成)
26 | 19/07/2026 | Executive Office 2 - Faceplate installed (面板安装)
27 | 19/07/2026 | Executive Office 2 - Test passed (测试通过)
28 | 19/07/2026 | Executive Office 2 - Labels completed (标签完成)
29 | 19/07/2026 | Executive Office 3 - Before cable pulling (穿线前)
30 | 19/07/2026 | Executive Office 3 - Cable pulling completed (穿线完成)
31 | 19/07/2026 | Executive Office 3 - Termination in progress (端接过程)
32 | 19/07/2026 | Executive Office 3 - Termination completed (端接完成)
33 | 19/07/2026 | Executive Office 3 - Faceplate installed (面板安装)
34 | 19/07/2026 | Executive Office 3 - Test passed (测试通过)
35 | 19/07/2026 | Executive Office 3 - Labels completed (标签完成)
36 | 19/07/2026 | Meeting Room - Before cable pulling (穿线前)
37 | 19/07/2026 | Meeting Room - Cable pulling completed (穿线完成)
38 | 19/07/2026 | Meeting Room - Termination in progress (端接过程)
39 | 19/07/2026 | Meeting Room - Termination completed (端接完成)
40 | 19/07/2026 | Meeting Room - Faceplate installed (面板安装)
41 | 19/07/2026 | Meeting Room - Test passed (测试通过)
42 | 19/07/2026 | Meeting Room - Labels completed (标签完成)

## Issue_RFA Log
ISSUE LOG
Project : |  | L35 Office Retrofit
Item No. | Date | Issue Description | Risk | Proposed solution | Action By | Completed Photos | Issue Open / Closed | Remarks
1 | 17/07/2026 | Cable routing conflict with existing HVAC ducting in Open Office area | Medium | Reroute cables via alternate pathway below ceiling tile | ShiHao Liu |  | Closed
2 | 18/07/2026 | Pending client sign-off for Executive Office 1 termination | Low | Schedule follow-up meeting with client PM | Dayne Chea |  | Open
Project : |  | Cooley Shanghai Meeting Room Retrofit
Item No. | Issued Date | RFI / RFA | Description | Issued to | Respond by |  | Issue Open / Closed | Remarks
1