## Progress Report
Progress Report Updated On : |  |  |  | 2026-07-30
Project : |  |  |  | Aurora Tech Shanghai - L28 Smart Office Retrofit
Aurora Tech Shanghai - L28 Smart Office Retrofit
Item No. | Description | Cable Pulling |  |  | Termination |  |  | Faceplate Installation |  |  | Testing |  |  | Overall Percentage
| Floor | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date
L28
1 | Reception | 100% | 2026-07-25 | 2026-07-25 | 80% | 2026-07-28 | 2026-07-30 | 50% | 2026-07-29 | 2026-07-31 | 0% |  | 2026-08-02
2 | Open Office | 80% | 2026-07-28 | 2026-07-30 | 30% | 2026-07-29 | 2026-08-01 | 0% |  | 2026-08-03 | 0% |  | 2026-08-05
3 | Meeting Room | 20% | 2026-07-29 | 2026-07-28 | 0% |  | 2026-08-02 | 0% |  | 2026-08-04 | 0% |  | 2026-08-06
Overall Percentage (%)
Coming Soon:- Targeted Progress on within this week
In Progress
Delay
Not Started
Completed

## Site Photo
Progress Report Updated On : |  |  | 2026-07-30
Project : |  |  | Aurora Tech Shanghai - L28 Smart Office Retrofit
Item No. | Date | Description | Photos
1 | 2026-07-30 | Before cable pulling / 穿线前
2 | 2026-07-30 | Cable pulling completed / 穿线完成
3 | 2026-07-30 | Termination in progress / 端接过程
4 | 2026-07-30 | Termination completed / 端接完成
5 | 2026-07-30 | Before cable pulling / 穿线前
6 | 2026-07-30 | Cable pulling completed / 穿线完成
7 | 2026-07-30 | Before cable pulling / 穿线前

## Issue_RFA Log
ISSUE LOG
Project : |  | Aurora Tech Shanghai - L28 Smart Office Retrofit
Item No. | Date | Issue Description | Risk | Proposed solution | Action By | Completed Photos | Issue Open / Closed | Remarks
1 | 2026-07-29 | Meeting Room cable tray routing conflicts with existing HVAC duct | Medium | Coordinate with MEP to reroute tray, propose alternative by 2026-07-31 | Cailleach |  | Open
RFI / RFA LOG
Project : |  | Aurora Tech Shanghai - L28 Smart Office Retrofit
Item No. | Issued Date | RFI / RFA | Description | Issued to | Respond by |  | Issue Open / Closed | Remarks
1 | 2026-07-30 | RFI | Request confirmation of final faceplate color (white vs ivory) | Aurora Tech PM | 2026-08-02 |  | Open