## Q&A
Aurora Tech Shanghai L28 Smart Office Retrofit
Survey Date: 30th Jul'26
Project Site Survey & Clarification
S/N | Tendo | (Client) to Confirm | Remark
1
1
IT Relocation -
Server Room:
Please confirm on the IT Equipment that is to be relocated or dispose in the "IT - Server Room" tab
Are we require to also handle on those that is required to be dispose?
Office Area:
Please confirm on the IT Equipment that is to be relocated or dispose in the "IT - Office Area" tab
Relocate and re-use of 50 sets of workstation IT Equipment, how do we handle for the remaining sets as there are more workstations in the current setup.
AV Relocation -
Office Area:
Please confirm on the AV Equipment that is to be relocated or dispose in the "AV - Office Area" tab
Are we require to also handle on those that is required to be dispose?
Security Relocation -
Server Room:
Please confirm on the Security Equipment that is to be relocated or dispose in the "Security - Server Room" tab
Are we require to also handle on those that is required to be dispose?
Office Area:
Please confirm on the Security Equipment that is to be relocated or dispose in the "Security - Office Area" tab
New Security Cabling:
If the above is to be relocated and reuse, do we propose for new security cabling for both the CCTV and Door Access in our scope?
Others -
Looking at the existing IT Equipment in the Server Room that is live and planned to be relocated and reuse in the new office, 2 Racks are required to house these Equipment and the New Cabling. Therefore, we will suggest to purchase for a new rack and reuse an existing rack. Please confirm.
22 | Do we also have to cover the scope on re-instatement of the existing office on the IT / AV / Security portion? (Tearing out of the cabling, remaining racks, IT / AV / Security Equipment and etc.)