## Progress Report
Progress Report Updated On : |  |  |  | 2026-07-30
Project : |  |  |  | Aurora Tech - L28 Smart Office Retrofit
Aurora Tech - L28 Smart Office Retrofit
Item No. | Description | Cable Pulling |  |  | Termination |  |  | Faceplate Installation |  |  | Testing |  |  | Overall Percentage
| Floor | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date | % | Till Date | Target Date
L28
1 | Reception | 1 | 2026-07-25 | 2026-07-25 | 0.8 | 2026-07-28 | 2026-07-30 | 0.5 | 2026-07-29 | 2026-07-31 | 0 |  | 2026-08-02 | 0.575
2 | Open Office | 0.8 | 2026-07-28 | 2026-07-30 | 0.3 | 2026-07-29 | 2026-08-01 | 0 |  | 2026-08-03 | 0 |  | 2026-08-05 | 0.275
3 | Meeting Room | 0.2 | 2026-07-29 | 2026-07-28 | 0 |  | 2026-08-02 | 0 |  | 2026-08-04 | 0 |  | 2026-08-06 | 0.05
Overall Percentage (%)
|  | 66.67% | 2026-07-17 | 2026-07-17 | 36.67% | 2026-07-17 | 2026-07-17 | 16.67% | 2026-07-19 | 2026-07-19 | 0% | 2026-07-19 | 2026-07-19 | 30%
Coming Soon:- Targeted Progress on within this week
In Progress
Delay
Not Started
Completed

## Site Photo
Progress Report Updated On : |  |  | 20/07/2026
Project : |  |  | Cooley Shanghai Meeting Room Retrofit
Item No. | Date | Description | Photos
1 | 17/07/2026 | Reception Area - Before cable removal (前台区域工位布线拆除前)
2 | 17/07/2026 | Reception Area - Cable removal in progress (拆除过程中)
3 | 17/07/2026 | Reception Area - Cable labelled & coiled under floor (线缆整理标记盘放地板下)
4 | 19/07/2026 | Reception Area - Cable termination T568B (线缆端接)
5 | 19/07/2026 | Reception Area - Continuity test passed (通断测试通过)
6 | 19/07/2026 | Reception Area - Panel installed with labels (面板安装+标签)
7 | 19/07/2026 | New points for wiring(新增点位穿线)
8 | 19/07/2026 | Side Door - New card reader installed by security vendor (安防新增读卡器)
9 | 19/07/2026 | Side Door - Security cable relocation assisted (协助安防线缆移线)
10 | 20/07/2026 | System commissioning & test (系统试运行)
11 | 20/07/2026 | Completion documentation (竣工资料编制)

## Issue_RFA Log
ISSUE LOG
Project : |  | L28 Retrofit
Item No. | Date | Issue Description | Risk | Proposed solution | Action By | Completed Photos | Issue Open / Closed | Remarks
1 | 2026-07-29 | Meeting Room cable tray routing conflicts with HVAC duct | Medium | Coordinate with MEP to reroute | Cailleach |  | Open
RFI / RFA LOG
Project : |  | L28 Retrofit
Item No. | Issued Date | RFI / RFA | Description | Issued to | Respond by |  | Issue Open / Closed | Remarks
1 | 2026-07-30 | RFI | Confirm final faceplate color | Aurora Tech PM | 2026-08-02 |  | Open